## Cihan
Waterfall Gantt Chart Of The Stefano Shop
Project Title: | Stefano Digitization |  | Start Date: |  | 2024-11-04
Project Manager: | Cihan BOZER |  | Estimated Completion Date: |  | 2024-12-23
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 45 |  |  |  |  | WEEK 46 |  |  |  |  | WEEK 47 |  |  |  |  | WEEK 48 |  |  |  |  | WEEK 49 |  |  |  |  | WEEK 50 |  |  |  |  | WEEK 51 |  |  |  |  | ADD WEEKS AS NEEDED
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Phase/Milestone
Project Kickoff | Cihan | 2024-11-04 | 2024-11-04 | 1 | bar: WEEK 45 M
Build storefront | Aliyah | 2024-11-04 | 2024-11-15 | 10 | bar: WEEK 45 M to WEEK 46 F
Create social media channels | Taylor | 2024-11-11 | 2024-11-15 | 5 | bar: WEEK 46 M to WEEK 46 F
Status Report | Cihan | 2024-11-18 | 2024-11-18 | 1 | bar: WEEK 47 M
Input inventory data | Moe | 2024-11-18 | 2024-11-22 | 5 | bar: WEEK 47 M to WEEK 47 F
Build social media integration | Aliyah | 2024-11-18 | 2024-11-29 | 10 | bar: WEEK 47 M to WEEK 48 F
Status Report | Cihan | 2024-11-25 | 2024-11-25 | 1 | bar: WEEK 48 M
Train Stefano's on platform | Moe | 2024-11-25 | 2024-11-29 | 5 | bar: WEEK 48 M to WEEK 48 F
Build recommendation engine | Aliyah | 2024-12-02 | 2024-12-13 | 10 | bar: WEEK 49 M to WEEK 50 F
Status Report | Cihan | 2024-12-02 | 2024-12-02 | 1 | bar: WEEK 49 M
Create custom sales report | Moe | 2024-12-11 | 2024-12-17 | 5 | bar: WEEK 50 W to WEEK 51 T
Documentation | Cihan | 2024-12-18 | 2024-12-19 | 2 | bar: WEEK 51 W to WEEK 51 Tr
Closure | Cihan | 2024-12-20 | 2024-12-20 | 1 | bar: WEEK 51 F
Add Phase/Milestone As Needed
[add tasks as needed]
Her görev tasarım, oluşturma, test etme ve yayınlamayı içerir
Mühendislik Müdürü | Aliyah
Satıcı Yöneticisi | Moe
Pazarlama Müdürü | Taylor

## Sheet1
Waterfall Gantt Chart Template
Project Title: | [write title] |  | Start Date: |  | [dd/mm/yyyy]
Project Manager: | [your name] |  | Estimated Completion Date: |  | [dd/mm/yyyy]
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | ADD WEEKS AS NEEDED
[5 empty] | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F | M | T | W | Tr | F
Phase/Milestone
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days] | WEEK 1 M: Shade days to match task dates
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
[task] | [assignee] | [dd/mm/yyyy] | [dd/mm/yyyy] | [number of days]
Add Phase/Milestone As Needed
[add tasks as needed]